## University Park
UNIVERSITY PARK CAMPUS 2016
BUILDING NAME | PSU Proj.# | Permit # | Bldg.# | Description | Status | Date Sent to L&I | Date Returned | Level of Permit | Design Services / Outside Designer
3058 Research Dr. | 00-04264.01 |  | N/A | MECH Reno for Fenske Swing Space | Pending | 2016-11-15 |  | 2 | OD
Academic Projects | 00-00471.04 | 201601339 | 0407-000 | Fire Protection Backflow Prevention | Building Permit |  | 2016-09-29 | 2 | OD | Rob Bloom
Ag Arena | 00-00471.04 | 201601348 | 0130-000 | Fire Protection Backflow Prevention | Building Permit |  | 2016-09-29 | 2 | OD | Rob Bloom
Ag Engineering | 00-03437.00 | 201601025 | 0114-000 | Building Partial Demo | Demo Permit |  | 2016-07-15 | Demo | OD | Jeff Spackman
Ag Hill Chiller Bldg | 00-03437.00 |  | 0941-000 | Office Renovations | Rejected | 2016-04-08 | 2016-04-26 | 2 | OD
Ag Hill Chiller Bldg | 00-03437.00 | 201600825 | 0941-000 | Office Fit Out - Resubmission | C of O |  | 2016-06-14 | 2 | OD | Jeff Spackman
Ag Science and Industries | 00-01266.00 | 201600684 | 0116-000 | Roof Replacement and Fall Protection | Building Permit | 2016-04-29 | 2016-05-16 | 2 | DS | Christie Pace
Althouse Lab | 00-03800.00 | 201600780 | 0411-000 | Standby Power for Critical Research Equipment | Building Permit |  | 2016-06-06 | 2 | OD | Chris Hampton
Arts Cottage | 00-00471.04 | 201601349 | 0102-000 | Fire Protection Backflow Prevention | Building Permit |  | 2016-09-29 | 2 | OD | Rob Bloom
ARL West I | 00-05206.00 | 201601201 | 0996-019 | Cold Spray Room Alterations | Building Permit | 2016-08-12 | 2016-08-30 | 2 | OD | Jeff Spackman
ARL West III | 00-04768.00 | 201600201 | 0066-000 | 1st Floor Research Area Renovations | Building Permit |  | 2016-02-22 | 2 | OD | Jeff Spackman
ARL West III | 00-04655.00 | 201600750 | 0066-000 | Existing Equipment Relocation | Building Permit | 2016-05-11 | 2016-05-26 | 2 | OD | Jeff Spackman
Applied Science | 00-04686.00 | 201600451 | 0996-009 | Campus Chilled Water Connection | Building Permit | 2016-03-24 | 2016-04-08 | 2 | OD | Jeff Spackman
Applied Science | 00-04655.00 | 201600622 | 0996-009 | Electrical Upgrades for Dynamic Test Bed | Building Permit | 2016-04-22 | 2016-05-13 | 2 | OD | Jeff Spackman
Armsby | 00-04743.00 |  | 0101-000 | Campus Chilled Water Connection | Rejected | 2016-03-02 | 2016-03-30 | 1 | DS
Armsby | 00-04743.00 | 201600494 | 0101-000 | Campus Chilled Water Connect (completed under 00-04841.00) | C of O | 2016-04-06 | 2016-04-12 | 2 | OD
Arts Building | 00-04262.00 | 201690474 | 0751-000 | Stage Curtain Replacement | C of C | 2016-04-07 | 2016-05-16 | 1 | DS
Atherton Hall | 00-04634.00 | 201600661 | 0233-000 | Phase 4 SE Sector Reno | Building Permit | 2016-02-01 | 2016-05-13 | 2 | OD | Rich O'Donald
Atherton Hall | 00-04634.00 | 201601091 | 0233-000 | Phase 4 SE Sector Reno - Sprinkler | C of O |  | 2016-08-03 | 2 | OD
Atherton Hall | 00-04634.00 | 201601116 | 0233-000 | Phase 4 SE Sector Reno - Fire Alarm | C of O |  | 2016-08-08 | 2 | OD
Beaver Stadium | 00-04516.00 | 201600104 | 0812-000 | Fire Platforms and Fall Protection | Building Permit |  | 2016-02-04 | 2 | OD
Beaver Stadium | 00-04533.00 | 201600985 | 0812-000 | MEP Maintenance | Building Permit | 2016-07-01 | 2016-07-08 | 2 | OD
Beaver Stadium | 00-05072.00 | 201601401 | 0812-000 | AT&T Distributed Antenna System | Building Permit | 2016-10-04 | 2016-10-14 | 2 | OD | Terry Hansel
Boucke | 00-04032.00 | 201601002 | 0013-000 | Room 220 Renovation | Building Permit | 2016-06-30 | 2016-07-13 | 2 | DS
Bryce Jordan Center | 00-03890.00 | 201600404 | 0045-000 | Arena, House and Sports Lighting Upgrades | Building Permit | 2016-03-16 | 2016-03-30 | 2 | OD | Nate Patrick
Bryce Jordan Center | 00-03890.00 | 201600885 | 0045-000 | Arena, House and Sports Lighting Upgrades - Revision | Building Permit |  | 2016-06-20 | 2 | OD | Nate Patrick
Bryce Jordan Center | 00-03890.00 | 201601204 | 0045-000 | Arena & House Emergency Ergress Lighting | Building Permit |  | 2016-08-30 | 2 | OD | Nate Patrick
Bryce Jordan Center | 00-04609.00 | 201600656 | 0045-000 | Misc. Electrical Upgrades | C of O | 2016-04-29 | 2016-05-11 | 2 | OD
Bryce Jordan Center | 00-04609.00 | 201600878 | 0045-000 | Misc. Electrical Upgrades - Fire Alarm | C of O |  | 2016-06-23 | 2 | OD
Bryce Jordan Center | 00-00972.00 | 201601041 | 0045-000 | Install AT&T Wireless Network | C of O |  | 2016-07-20 | 2 | OD | Matt Vail
Burrowes | 00-01526.00 | 201600045 | 0601-000 | Deffered Fire Alarm - Resubmission | Building Permit |  | 2016-01-18 | 2 | OD
Business Bldg | 00-04906.00 | 201600604 | 0023-001 | Room 203 Renovation | Building Permit | 2016-04-15 | 2016-05-03 | 2 | DS
Career Services | 00-04998.00 | 201600946 | 0042-000 | 3rd Floor Office Reno | Building Permit | 2016-06-21 | 2016-07-01 | 2 | OD
Chambers | 00-03633.00 | 201600769 | 0602-000 | Black Box Classroom 221 | Building Permit | 2016-05-17 | 2016-05-26 | 2 | OD | Jess Dubler
Chambers | 00-03633.00 | 201601001 | 0602-000 | Black Box Classroom 221 - 2nd Phased Approval | Building Permit | 2016-07-01 | 2016-07-14 | 2 | OD | Jess Dubler
Chambers | 00-03633.00 | 201601138 | 0602-000 | Black Box Classroom 221 - Partial Occupancy | C of O | 2016-08-09 | 2016-08-18 | 2 | OD | Jess Dubler
Chambers | 00-04263.00 | 201601254 | 0602-000 | Dean Conference Room 228 | Building Permit | 2016-08-31 | 2016-09-09 | 2 | OD | Jess Dubler
Data Center | 00-01954.00 | 201601326 | 0043-000 | New Bldg - Phase 1B | Building Permit |  | 2016-10-03 | 2 | OD | Monica Reed
Davey | 00-04749.00 | 201601190 | 0412-000 | ME Equipment Maintenance Access | Building Permit | 2016-08-16 | 2016-08-24 | 2 | OD | Jess Dubler
Davey | 00-05027.00 | 201601277 | 0412-000 | Room 135 Reno | Building Permit | 2016-09-09 | 2016-09-15 | 2 | OD
Davey | 00-04792.00 | 201601498 | 0412-000 | Room 35 Reno | Building Permit |  | 2016-11-15 | 2 | OD | Jess Dubler
Dry Storage | 00-03971.00 | 201600840 | 0049-000 | Building Reno - Revisions | C of O |  | 2016-06-16 | 2 | OD
Earth & Engineering Sciences | 00-03341.00 | 201600318 | 0035-000 | ESP - Lab Energy Retrofits | C of O |  | 2016-03-14 | 2 | OD | Nate Patrick
East Area Locker Room | 00-00471.04 | 201601351 | 0836-000 | Fire Protection Backflow Prevention | Building Permit |  | 2016-09-29 | 2 | OD | Rob Bloom
East Campus Steam Plant | 00-04689.00 | 201600562 | 0910-000 | DA2 Tank Maintenance Platform | Building Permit | 2016-04-12 | 2016-05-02 | 2 | OD
East Halls New Residences | 00-03925.00 | 201600198 | 0261-000 | New Residence Structure | Building Permit | 2016-02-05 | 2016-02-22 | 2 | OD
East Parking Deck | 00-05038.00 | 201600816 | 0995-087 | Electrical and Communication Renovations | C of O | 2016-05-23 | 2016-06-09 | 2 | OD
Engineering Unit C | 00-04919.00 | 201600706 | 0307-000 | Room 101 Alterations | Building Permit |  | 2016-06-06 | 2 | OD
Eisenhower Auditorium | 00-03894.00 | 201600075 | 0011-000 | Entrance Canopy Signage | Building Permit | 2016-01-13 | 2016-01-27 | Sign | DS
Eisenhower Auditorium | 00-04253.00 | 201690598 | 0011-000 | Fire Curtain Replacement | Building Permit | 2016-05-18 | 2016-06-07 | 1 | DS
Eisenhower Parking Deck | 00-04268.00 |  | 0940-000 | Parking Office Renovations | Rejected | 2016-02-23 | 2016-03-15 | 2 | DS
Eisenhower Parking Deck | 00-04268.00 | 201600434 | 0940-000 | Parking Office Renovations - Resubmission | C of O | 2016-03-23 | 2016-04-06 | 2 | DS
Eisenhower Parking Deck | 00-05038.00 | 201600814 | 0940-000 | Electrical and Communication Renovations | C of O | 2016-05-23 | 2016-06-09 | 2 | OD
Electrical Engineering West | 00-04605.00 | 201600195 | 0302-000 | Room 6A Conversion into a Lab - Revision | C of O | 2016-02-04 | 2016-02-22 | 2 | DS
Electrical Engineering West | 00-04947.00 | 201601303 | 0302-000 | Basement Process Water System | Building Permit | 2016-09-19 | 2016-09-26 | 2 | DS | Nevienne Manning
Farm Services | 00-03437.01 | 201600841 | 0130-011 | Additional Equipment | C of O | 2016-06-01 | 2016-06-16 | 2 | OD
Fenske | 00-04264.00 | 201601419 | 0405-000 | Demo of existing building | Building Permit | 2016-10-06 | 2016-10-21 | Demo | DS | Dwayne Rush
Field Maintenance Facility | 00-03406.00 | 201600749 | 0945-000 | New Field Maintenance Storage Facility | Building Permit |  | 2016-06-07 | 2 | OD
Findlay Commons | 00-03925.00 | 201600258 | 0277-000 | Ph 1A Tunnels Reno | Building Permit | 2016-02-05 | 2016-03-02 | 2 | OD
Findlay Commons | 00-03925.00 | 201600459 | 0277-000 | Dining Hall - Sprinkler | Building Permit |  | 2016-04-29 | 2 | OD
Findlay Commons | 00-03925.00 |  | 0277-000 | Dining Hall - Fire Alarm | Rejected |  | 2016-07-07 | 2 | OD
Findlay Commons | 00-03925.00 | 201601077 | 0277-000 | Dining Hall - Fire Alarm | Building Permit |  | 2016-07-28 | 2 | OD
Findlay Commons | 00-03513.00 |  | 0277-000 | Building Reno - Ph 1 & 2 Partial Occupancy | Rejected | 2016-07-07 | 2016-07-19 | 2 | OD
Findlay Commons | 00-03513.00 | 201601081 | 0277-000 | Building Reno - Ph 1 & 2 Partial Occupancy | C of O | 2016-07-22 | 2016-07-29 | 2 | OD
Findlay Commons | 00-03513.00 |  | 0277-000 | Building Reno - Ph 3 Partial Occupancy | Rejected | 2016-07-07 | 2016-07-19 | 2 | OD
Findlay Commons | 00-03513.00 | 201601082 | 0277-000 | Building Reno - Ph 3 Partial Occupancy | Building Permit | 2016-07-22 | 2016-07-29 | 2 | OD
Findlay Commons | 00-03513.00 | 201601502 | 0277-000 | Building Reno - C-Store Partial Occupancy | Building Permit | 2016-10-31 | 2016-11-18 | 2 | OD | Rich O'Donald
Findlay Commons | 00-03513.00 | 201601504 | 0277-000 | Building Reno - Elevator Partial Occupancy | Building Permit | 2016-10-31 | 2016-11-18 | 2 | OD | Rich O'Donald
Fisher Hall | 00-03925.00 | 201690166 | 0260-000 | Partition Walls for Office Space | C of C | 2016-01-29 | 2016-02-29 | 1 | DS
Fisher Hall | 00-03925.00 | 201600257 | 0260-000 | Phase 1A Building Reno | Building Permit | 2016-02-05 | 2016-03-02 | 2 | OD
Food Science | 00-03342.00 |  | 0107-001 | Condenser Fan Upgrade | Rejected | 2016-04-06 | 2016-04-26 | 2 | OD
Food Science | 00-03342.00 | 201600663 | 0107-001 | Condenser Fan Upgrade - Resubmission | C of O | 2016-05-02 | 2016-05-11 | 2 | OD | Nevienne Manning
Ford | 05-92438.00 | 201600845 | 0023-000 | County Emergency Antenna Relocation | Building Permit | 2016-06-03 | 2016-06-20 | 2 | OD
Grange | 00-03781.00 | 201600606 | 0232-000 | Undergraduate Studies Areas Renovations | Building Permit | 2016-04-15 | 2016-05-02 | 2 | DS
Grange | 00-03781.00 | 201601015 | 0232-000 | Undergraduate Studies Areas - Basement Partial Occup. | C of O | 2016-07-06 | 2016-07-19 | 2 | DS
Grange | 00-03781.00 | 201601121 | 0232-000 | First Floor Reno | Building Permit |  | 2016-08-04 | 2 | OD
Greenberg Indoor Sports Complex | 00-04184.00 | 201600038 | 0835-000 | Morgan Academic Center - First Flr Parital Occup | C of O | 2015-12-17 | 2016-01-13 | 2 | DS
Greenberg Indoor Sports Complex | 00-04184.00 | 201600643 | 0835-000 | Morgan Academic Center - Structural Revisions | Building Permit | 2016-04-15 | 2016-05-11 | 2 | OD
Greenberg Indoor Sports Complex | 00-04264.01 | 201600379 | 0835-000 | Ground Floor Reno for Fenske Swing Space | Building Permit |  | 2016-03-24 | 2 | OD | Brian Hayes
Greenberg Indoor Sports Complex | 00-04264.01 | 201601172 | 0835-000 | Ground Floor Reno for Fenske Swing Space - Fire Alarm | C of O |  | 2016-08-24 | 2 | OD | Brian Hayes
Greenberg Indoor Sports Complex | 00-04264.01 | 201600709 | 0835-000 | First Floor Reno for Fenske Swing Space | C of O | 2016-05-03 | 2016-05-20 | 2 | OD | Brian Hayes
Greenberg Indoor Sports Complex | 00-04264.01 | 201601269 | 0835-000 | Ground Floor Reno for Fenske Swing Space - Partial Occp | C of O |  | 2016-09-15 | 2 | OD | Brian Hayes
Greenberg Indoor Sports Complex | 00-04264.01 | 201601270 | 0835-000 | First Floor Reno for Fenske Swing Space - Partial Occup | C of O |  | 2016-06-15 | 2 | OD | Brian Hayes
Greenberg Indoor Sports Complex | 00-05179.00 |  | 0835-000 | Occupancy Reevaluation | Pending | 2016-11-06 |  | 2 | OD
Greenhouse H | 08-03652.00 | 201601006 | 0155-000 | Building Documentation - As Builts Plan Revision | C of O | 2016-07-01 | 2016-07-15 | 2 | DS
Greenhouse J | 08-03652.00 |  | 0157-000 | Building Renovation | Rejected |  | 2016-09-20 | 2 | OD
Hallowell | 00-00471.04 | 201601332 | 0317-000 | Fire Protection Backflow Prevention | Building Permit |  | 2016-09-29 | 2 | OD | Rob Bloom
Hamilton Hall | 00-04991.00 | 201601458 | 0205-000 | Lounge Renovation | Building Permit | 2016-10-17 | 2016-11-02 | 2 | OD | Matt Vail
Hammond | 00-04883.00 | 201600687 | 0304-000 | Room 17 Renovation | C of O | 2016-04-27 | 2016-05-16 | 2 | OD
Hammond | 00-04939.00 | 210601382 | 0304-000 | Room 234 Renovation | Building Permit | 2016-09-27 | 2016-10-06 | 2 | OD | Brian Hayes
Hammond | 00-04870.00 |  | 0304-000 | Curtain Wall Replacement | Pending | 2016-11-10 |  | 2 | OD
Hastings Hall | 00-04710.00 | 201600202 | 0252-000 | Elevator Modernization | C of O | 2016-02-05 | 2016-02-22 | 2 | OD
Henderson North | 00-04458.00 | 201600110 | 0651-000 | Avatar Lab Rm 230-232 Reno | Building Permit | 2016-01-19 | 2016-02-03 | 2 | DS
Henderson North | 00-04458.00 |  | 0651-000 | Avatar Lab - Partial Occupancy | Rejected | 2016-07-08 | 2016-07-19 | 2 | DS | Brian Hayes
Henderson North | 00-04458.00 | 201601076 | 0651-000 | Avatar Lab - Partial Occupancy - Resubmission | Building Permit | 2016-07-19 | 2016-07-29 | 2 | DS | Brian Hayes
Henderson North | 00-04458.00 | 201601191 | 0651-000 | Avatar Lab - Construction Type Change | Building Permit | 2016-08-15 | 2016-08-30 | 2 | DS | Brian Hayes
Holuba Hall | 00-04021.00 | 201600518 | 0833-000 | Overhead Door | Building Permit | 2016-04-11 | 2016-04-13 | 2 | OD
Holuba Hall | 00-00471.04 | 201601336 | 0833-000 | Fire Protection Backflow Prevention | Building Permit |  | 2016-09-29 | 2 | OD | Rob Bloom
Housing & Food Service | 00-03261.00 | 201690006 | 0280-000 | Warehouse & Bakery Expansion - Roof Replacement | Building Permit | 2016-01-04 | 2016-01-13 | 1 | OD
Housing & Food Service | 00-03261.00 | 201600152 | 0280-000 | Warehouse/Bakery - Partial Occup 5 Dry Dock | Building Permit |  | 2016-02-16 | 2 | OD
Housing & Food Service | 00-03261.00 | 201600151 | 0280-000 | Warehouse/Bakery - Partial Occup 7 | Building Permit |  | 2016-02-16 | 2 | OD
Housing & Food Service | 00-03261.00 | 201600440 | 0280-000 | Warehouse/Bakery - Offices Revision | Building Permit | 2016-03-14 | 2016-04-06 | 2 | OD
HUB | 00-04914.00 | 201600867 | 0005-000 | Locker Room Renovations | C of O | 2016-04-07 | 2016-06-20 | 2 | OD
HUB Parking Deck | 00-05038.00 | 201600812 | 0995-080 | Electrical and Communication Renovations | C of O | 2016-05-23 | 2016-06-09 | 2 | OD
Indoor Multisport Facility | 00-03430.00 | 201600851 | 0846-000 | Roof Access | Building Permit | 2016-06-01 | 2016-06-20 | 2 | OD
IM | 00-04421.00 | 201600169 | 0804-000 | Phase III Building Renovation & Addition | Building Permit |  | 2016-02-17 | 2 | OD | Marv Bevan
IM | 00-04421.00 | 201601324 | 0804-000 | Phase III Building Renovation & Addition - Fire Alarm | Building Permit |  | 2016-09-28 | 2 | OD | Marv Bevan
IST | 00-04902.00 | 201601199 | 0039-000 | Heating Improvements for Corridors | Building Permit | 2016-08-16 | 2016-08-24 | 2 | DS | Derek Leonard
James | 00-04660.00 | 201601278 | 0998-027 | Third Floor Renovation | Building Permit | 2016-08-22 | 2016-09-15 | 2 | DS
Johnston Hall | 00-04780.00 | 201690502 | 0276-000 | Roof Replacement | Building Permit | 2016-05-03 | 2016-05-20 | 1 | DS
Jordan Hall | 00-04382.00 | 201600333 | 0202-000 | Bathroom Renovations | C of O | 2016-03-08 | 2016-03-17 | 2 | OD
Jordan Hall | 00-04382.00 | 201601092 | 0202-000 | Bathroom Renovations - Sprinklers | C of O |  | 2016-08-04 | 2 | OD
Jordan Hall | 00-04382.00 | 201601170 | 0202-000 | Bathroom Reno - Fire Alarm | C of O |  | 2016-08-18 | 2 | OD
Keller | 00-04949.00 | 201600557 | 0015-000 | Golf Lab Renovations | Building Permit | 2016-04-13 | 2016-04-26 | 2 | OD
Kern | 00-04927.00 | 201600651 | 0452-000 | 4th Floor Office Renovation | C of O | 2016-04-20 | 2016-05-09 | 2 | OD
Kern | 00-04927.00 | 201601004 | 0452-000 | Water Cooler Relocation | C of O | 2016-07-06 | 2016-07-15 | 2 | OD
Lasch | 00-04195.00 | 201600065 | 0845-000 | Locker/Equipment Room Reno | C of O |  | 2016-01-19 | 2 | OD
Lasch | 00-04195.00 | 201600499 | 0845-000 | Locker/Equipment Room Reno - Fire Alarms | C of O |  | 2016-04-15 | 2 | OD
Lasch | 00-04195.00 | 201600665 | 0845-000 | Locker/Equipment Rm Reno - Sprinkler Revision | C of O |  | 2016-05-25 | 2 | OD
Lasch | 00-04195.00 | 201600328 | 0845-000 | Locker/Equipment Rm Reno - Partial Sprinkler | Building Permit |  | 2016-06-02 | 2 | OD
Lasch | 00-04195.00 | 201600793 | 0845-000 | Locker/Equipment Rm Reno - Fire Alarm | C of O |  | 2016-06-07 | 2 | OD
Lasch | 00-04195.00 | 201600963 | 0845-000 | Locker/Equipment Room Reno - Area Revision | C of O | 2016-06-09 | 2016-07-01 | 2 | OD
Lasch | 00-04195.00 | 201600852 | 0845-000 | Locker/Equipment Room Reno - Partial Occupancy | C of O |  | 2016-06-23 | 2 | OD
Lasch | 00-04195.00 | 201601062 | 0845-000 | Locker/Equipment Room Reno - Hot Tub Lift | C of O |  | 2016-07-27 | 2 | OD
Leonhard | 00-04928.00 | 201601122 | 0319-000 | Area 335 Renovation | Building Permit | 2016-08-01 | 2016-08-09 | 2 | OD | Brian Hayes
Leonhard | 00-05147.00 | 201601404 | 0319-000 | Area 315 Renovation | Building Permit | 2016-09-27 | 2016-10-14 | 2 | OD | Brian Hayes
Materials Research Institute | 00-04688.00 | 201600168 | 0965-002 | Room 133 Renovations | Building Permit | 2016-01-22 | 2016-02-17 | 2 | OD
Materials Research Institute | 00-04688.00 | 201600299 | 0965-002 | Room 133 - Plumbing, Electrical & HVAC | C of O | 2016-02-29 | 2016-03-10 | 2 | OD
Materials Research Institute | 00-04688.00 | 201600351 | 0965-002 | Room 127 & 128 Reno | Building Permit | 2016-03-08 | 2016-03-22 | 2 | OD
Materials Research Lab | 04-10538.00 | 201600500 | 0017-000 | Capital Renewal Reno - Bathroom/Shower Revision | Building Permit | 2016-04-04 | 2016-04-15 | 2 | DS
Materials Research Lab | 04-10538.00 |  | 0017-000 | Rooftop Fall Protection | Pending | 2016-10-31 |  | 2 | OD | Sean Walker
McCoy Natatorium | 01-02630.15 | 201600508 | 0820-000 | ICA Single Point Entry Access Modifications - Resubmission | Building Permit | 2015-04-04 | 2016-04-15 | 2 | DS
McElwain Hall | 00-04711.00 | 201600487 | 0240-000 | Recreation Room Renovation | C of O | 2016-03-31 | 2016-04-12 | 2 | OD
McKee Hall | 00-04714.00 | 201690500 | 0206-000 | Lounge Room Roof Replacement | Building Permit | 2016-05-03 | 2016-05-16 | 1 | DS
Millennium Science Complex | 00-05245.00 | 201601420 | 0038-001 | Convert N338 into Office/Conference Area | Building Permit | 2016-10-07 | 2016-10-25 | 2 | DS | Jason Smith
Mueller Lab | 00-0418600 | 201601481 | 0409-000 | Growth Room | Building Permit |  | 2016-11-15 | 2 | OD | Jess Dubler
Nittany Community Center | 00-04708.00 | 201600611 | 0215-050 | Room 101 & 108 Reno | C of O | 2016-04-21 | 2016-04-29 | 2 | OD
Nittany Hall #60 | 00-04708.00 |  | 0215-060 | Room 120 Reno | Rejected | 2016-04-21 |  | 2 | OD | Matt Vail
Nittany Hall #60 | 00-04708.00 | 201600778 | 0215-060 | Room 120 Reno - Resubmission | C of O |  | 2016-06-01 | 2 | OD | Matt Vail
Nittany Parking Deck | 00-05038.00 | 201600815 | 0995-060 | Electrical and Communication Renovations | C of O | 2016-05-23 | 2016-06-09 | 2 | OD
North American Refractories Bldg | 00-04504.00 | 201600416 | 0064-000 | Compressed Air System Modification | C of O | 2016-03-15 | 2016-04-06 | 2 | DS
North American Refractories Bldg | 00-04767.00 | 201600634 | 0064-000 | Start Lab 2nd Air Compressor | C of O | 2016-04-14 | 2016-05-11 | 2 | OD
North American Refractories Bldg | 00-04767.00 | 201600935 | 0064-000 | Start Lab 2nd Air Compressor - Revision | C of O |  | 2016-06-28 | 2 | OD
North American Refractories Bldg | 00-05093.00 | 201601302 | 0064-000 | Start Lab II Reno | Building Permit | 2016-09-16 | 2016-09-26 | 2 | OD | Dwayne Rush
North Halls New Residence | 00-03928.00 |  | 0214-100 | North Hall New Residence | Rejected | 2016-03-03 | 2016-03-15 | 2 | OD
North Halls New Residence | 00-03928.00 | 201600456 | 0214-100 | North Hall New Residence - Resubmission | Building Permit | 2016-03-24 | 2016-04-07 | 2 | OD
Nursing Sciences (formerly HHD) | 00-04237.00 | 201600787 | 0653-000 | Nursing Sciences Clinic Renovation | Building Permit | 2016-05-18 | 2016-06-03 | 2 | OD | Rachel Prinkey
Nursing Sciences (formerly HHD) | 00-04237.00 | 201601202 | 0653-000 | MEP Renovation | Building Permit | 2016-08-11 | 2016-08-24 | 2 | OD | Rachel Prinkey
Nursing Sciences (formerly HHD) | 00-04237.00 | 201601171 | 0653-000 | Nursing Sciences Clinic - Partial Occupancy | C of O | 2016-08-15 | 2016-08-18 | 2 | OD | Rachel Prinkey
Nursing Sciences (formerly HHD) | 00-04237.00 | 201601211 | 0653-000 | Entrance Addition | Building Permit | 2016-08-12 | 2016-08-26 | 2 | OD | Rachel Prinkey
Nursing Sciences (formerly HHD) | 00-04237.00 | 201601283 | 0653-000 | Nursing Sciences Clinic - Revision | Building Permit | 2016-09-12 | 2016-09-19 | 2 | OD | Rachel Prinkey
Nursing Sciences (formerly HHD) | 00-04237.00 | 201601403 | 0653-000 | Entrance Addition - Revision | Building Permit | 2016-10-04 | 2016-10-14 | 2 | OD | Rachel Prinkey
Old Main | 00-04743.00 | 201600311 | 0001-000 | Chilled Water System Repairs | Building Permit | 2016-03-02 | 2016-03-14 | 2 | DS | Rachel Prinkey
Old Main | 00-03865.00 | 201690597 | 0001-000 | Interior Stair Renovation | Building Permit | 2016-04-12 | 2016-06-07 | 1 | OD
Osmond | 00-04186.00 |  | 0401-000 | Room S22 & S22A Renovation | Rejected |  | 2016-01-11 | 2 | OD
Osmond | 00-05260.00 |  | 0401-000 | Rm 215 Cooling System | Pending | 2016-11-02 |  | 2 | DS
OPP Greenhouse Production 3 | 00-03940.00 |  | 0904-024 | New Hoop Structure | Rejected | 2016-08-02 | 2016-08-16 | 2 | DS
OPP Greenhouse Production 3 | 00-03940.00 | 201601271 | 0904-024 | New Hoop Structure Resubmission | Building Permit | 2016-09-07 | 2016-09-15 | 2 | DS
Outdoor Track | 00-04486.00 |  | 0995-033 | Track Improvements | Rejected | 2016-05-13 | 2016-08-31 | 2 | OD | Marv Bevan
Outdoor Track | 00-04486.00 | 201600884 | 0995-033 | Track Improvements - Resubmission | Building Permit |  | 2016-06-16 | 2 | OD | Marv Bevan
Outreach Innovation | 00-01820.00 | 201600273 | 0965-013 | Building Renovations - Revision Kitchenette | C of O | 2016-02-29 | 2016-03-10 | 2 | OD
Panofsky Hall | 00-04417.00 | 201600010 | 0270-006 | Fire Protection Renovations | C of O |  | 2016-01-12 | 2 | OD
Pattee | 00-05288.00 | 201601296 | 0003-000 | Pedestrian Underpass Ceiling Repairs | Building Permit | 2016-09-15 | 2016-09-23 | 2 | OD
Patterson | 00-04743.00 |  | 0121-000 | Campus Chilled Water Connection | Rejected | 2016-03-02 | 2016-03-30 | 1 | DS
Patterson | 00-04743.00 | 201600484 | 0121-000 | Campus Chilled Water Connect completed under (00-04841.00) | C of O | 2016-04-06 | 2016-04-12 | 2 | OD
Patterson | 00-00471.04 | 201601342 | 0121-000 | Fire Protection Backflow Prevention | Building Permit |  | 2016-09-29 | 2 | OD | Rob Bloom
Pavilion Theatre | 00-03052.00 | 201600683 | 0759-000 | Roof Replacement and Fall Protection | Building Permit | 2016-04-29 | 2016-05-16 | 2 | DS
Physical Plant Building | 00-03224.00 | 201600073 | 0904-000 | Snow Removal Platform - Resubmission | Building Permit | 2016-01-13 | 2016-01-27 | 2 | DS
Physical Plant Building | 00-04720.00 |  | 0904-000 | Solar Array Replacement | Rejected | 2016-01-29 | 2016-02-19 | 2 | DS
Physical Plant Building | 00-04720.00 |  | 0904-000 | Solar Array Replacement - Resubmission | Pending | 2016-03-02 |  | 2 | DS
Physical Plant Building | N/A | 201690186 | 0904-000 | Converting IT Open Area into an Office | C of C | 2016-02-02 | 2016-02-29 | 1 | DS
Physical Plant Building | 00-02552.00 | 201601098 | 0904-000 | Garage Auxiliary Office Suite 186 Reno | Building Permit | 2016-07-19 | 2016-08-02 | 2 | OD
Physical Plant Building | 00-00471.04 | 201601350 | 0904-000 | Fire Protection Backflow Prevention | Building Permit |  | 2016-09-29 | 2 | OD | Rob Bloom
Pollock Commons | 00-03157.00 | 201600582 | 0275-000 | HVAC Upgrades | Building Permit | 2016-04-07 | 2016-04-28 | 2 | OD | Matt Vail
Pollock Commons | 00-03157.00 | 201601118 | 0275-000 | HVAC Upgrades - Partial Occupancy | C of O |  | 2016-08-04 | 2 | OD | Matt Vail
Pollock Commons | 03-41457.23 | 201600889 | 0275-000 | Telecom HUB Site Electrical & HVAC Upgrades | Building Permit | 2016-06-14 | 2016-06-21 | 2 | OD | Chris Hampton
Porter Hall | 00-04709.00 | 201690470 | 0230-000 | Roof Replacement | Building Permit | 2016-04-28 | 2016-05-16 | 1 | DS
Pollock Building | 00-04411.02 | 201600685 | 0007-000 | Roof Replacement and Fall Protection | Building Permit | 2016-04-29 | 2016-05-16 | 2 | DS
Power Plant | 08-93143.00 |  | 0911-000 | Relocated Staff Swing Space | Rejected | 2016-09-23 | 2016-10-18 | 2 | OD | Jeff Spackman
Power Plant | 08-93143.00 |  | 0911-000 | Modular Staff Swing Space | Pending | 2016-11-02 |  | 2 | OD | Jeff Spackman
Reber | 00-04403.00 | 201600101 | 0303-000 | Lab 109 & 110 Reno | C of O | 2016-01-20 | 2016-02-09 | 2 | OD
Reber | 00-00507.00 | 201600806 | 0303-000 | HVAC Improvements | Building Permit |  | 2016-06-07 | 2 | OD
Reber | 00-05003.00 | 201601139 | 0303-000 | Lab 9 & 10 Renovations | Building Permit | 2016-08-01 | 2016-08-09 | 2 | OD | Dwayne Rush
Reber | 00-00471.04 | 201601341 | 0303-000 | Fire Protection Backflow Prevention | Building Permit |  | 2016-09-29 | 2 | OD | Rob Bloom
Reber | 00-04929.00 | 201601416 | 0303-000 | Student Commons | Building Permit |  | 2016-11-15 | 2 | OD | Brian Hayes
Rec Hall | 00-02473.00 | 201600693 | 0801-000 | Wrestling Hydrotherapy Room | Building Permit |  | 2016-06-03 | 2 | OD
Rec Hall | 01-02630.15 | 201601090 | 0801-000 | Single Point Entry Access - Sprinkler | Building Permit |  | 2016-08-03 | 2 | OD
Rec Hall | 01-02630.15 | 201601308 | 0801-000 | Single Point Entry Access - conference Rm Partial Occup | C of O | 2016-09-20 | 2016-10-04 | 2 | DS | Jason Smith
Rec Hall | 01-02630.15 |  | 0801-000 | Single Point Entry Access - Revision | Pending | 2016-11-15 |  | 2 | DS | Jason Smith
Research Building East | 00-00471.04 | 201601346 | 0028-000 | Fire Protection Backflow Prevention | Building Permit |  | 2016-09-29 | 2 | OD | Rob Bloom
Research Building East | 00-05014.00 | 201601424 | 0028-000 | Energy Saving Project | Building Permit | 2016-10-07 | 2016-10-18 | 2 | OD | Nevienne Manning
Research Building West | 00-00471.04 | 201601344 | 0271-000 | Fire Protection Backflow Prevention | Building Permit |  | 2016-09-29 | 2 | OD | Rob Bloom
Research Building West | 00-04320.00 | 201601430 | 0271-000 | Energy Saving Project | Building Permit | 2016-10-12 | 2016-10-21 | 2 | OD | Nate Patrick
Research Unit A Modular | 00-03437.01 | 201600979 | 0033-001 | Ag Engineering Swing Space - Revision | C of O | 2016-06-29 | 2016-07-12 | 2 | OD
Research Unit C | 00-04450.00 | 201600303 | 0032-000 | Mechanical & Electrical Renovations | C of O | 2016-02-29 | 2016-03-10 | 2 | OD
Research West | 00-04311.00 | 201600422 | 0271-000 | Room 111 Unit Replacement | Building Permit | 2016-03-15 | 2016-04-06 | 2 | OD
Research West | N/A | 201600621 | 0271-000 | Electrical Upgrades for CNC | Building Permit | 2016-04-22 | 2016-05-13 | 2 | OD
Rider | 00-04260.00 | 201600648 | 0998-072 | Switchgear Replacement | Building Permit | 2016-04-26 | 2016-05-06 | 2 | DS
Ritenour | 00-04174.00 | 201600586 | 0051-000 | East Wing Reno - Fire Alarms | Building Permit |  | 2016-05-03 | 2 | OD
Ritenour | 00-04174.00 |  | 0051-000 | East Wing Reno - Sprinklers | Rejected |  | 2016-07-19 | 2 | OD
Ritenour | 00-04174.00 | 201601148 | 0051-000 | East Wing Reno - Change of construction type to IIIB | Building Permit | 2016-08-02 | 2016-08-15 | 2 | OD
Ritenour | 00-04174.00 | 201601167 | 0051-000 | East Wing Reno - Sprinklers | Building Permit |  | 2016-08-16 | 2 | OD
Sackett | 00-02463.00 | 201601120 | 0301-000 | Cross Connect Renovations | Building Permit | 2016-08-01 | 2016-08-08 | 2 | OD | Jeff Spackman
Sackett | 00-03800.00 | 201601185 | 0301-000 | Standby Power for Critical Research Equipment | Building Permit |  | 2016-08-24 | 2 | OD | Chris Hampton
Sewage Pumping Station | 06-31310.08 | 201600978 | 0994-026 | East Campus Standby Generator Support Bldg Upgrades | C of O |  | 2016-07-13 | 2 | OD
Shields | 00-04811.00 | 201600848 | 0004-000 | Ground Floor Reno | Building Permit | 2016-05-27 | 2016-06-16 | 2 | DS | Pamela Garbini
Shields | 00-04811.00 | 201601058 | 0004-000 | Ground Floor Reno - Partial Occupancy | C of O | 2016-07-14 | 2016-07-27 | 2 | DS | Pamela Garbini
Shields | 00-04811.00 | 201601145 | 0004-000 | Ground Flr Reno - Bathroom Plan Revision | Building Permit | 2016-08-02 | 2016-08-12 | 2 | DS | Pamela Garbini
Shields | 00-02463.00 |  | 0004-000 | Cross Connect Renovations | Pending | 2016-11-06 |  | 2 | OD
Shulze Hall | 00-04712.00 | 201690501 | 0236-000 | Roof Replacement | Building Permit | 2016-05-03 | 2016-05-16 | 1 | DS
Simmons Hall | 00-04713.00 | 201690471 | 0241-000 | Roof Replacement | Building Permit | 2016-04-28 | 2016-05-16 | 1 | DS
South Chiller Building | 00-04841.00 | 201600450 | 0910-005 | Emergency Repair | Building Permit |  | 2016-04-08 | 2 | OD
Sparks | 00-03978.00 | 201600710 | 0701-000 | 3rd Floor HVAC Upgrades | C of O | 2016-05-11 | 2016-05-13 | 2 | OD
Sparks | 00-02436.00 | 201601444 | 0701-000 | Cross Connect Renovations | Building Permit |  | 2016-10-26 | 2 | OD | Rob Bloom
Steidle | 00-01306.00 | 201600112 | 0501-000 | Building Reno - Fire Alarm | C of O |  | 2016-02-03 | 2 | OD
Steidle | 00-01306.00 | 201600712 | 0501-000 | Building Reno - Partial Occupancy | C of O | 2016-04-28 | 2016-05-20 | 2 | OD
Stone Hall | 00-04633.00 | 201600203 | 0253-000 | Elevator Modernization | C of O | 2016-02-05 | 2016-02-22 | 2 | OD
Stuart Hall | 00-03925.00 | 201600551 | 0255-000 | Building Renovation - Resubmission | Building Permit |  | 2016-04-25 | 2 | OD
Supplemental Mail | 00-04832.00 | 201600681 | 0908-000 | Roof Replacement and Fall Protection | Building Permit | 2016-04-29 | 2016-05-16 | 2 | DS
Swine Research | 00-04979.00 | 201600928 | 0132-000 | Support Post Repairs/Replacement | Building Permit | 2016-06-15 | 2016-06-27 | 2 | DS
Thomas | 00-04264.01 | 201600260 | 0040-000 | Basement Reno for Fenske Swing Space | C of O | 2016-02-05 | 2016-03-07 | 2 | OD
Thomas | 00-04264.01 | 201600686 | 0040-000 | Basement Reno for Fenske Swing Space - Fire Alarm | Building Permit |  | 2016-05-24 | 2 | OD
Thomas | 00-04411.03 | 201600680 | 0040-000 | Roof Replacement and Fall Protection | Building Permit | 2016-04-29 | 2016-05-16 | 2 | DS
Tyson | 00-00471.04 | 201601340 | 0110-000 | Fire Protection Backflow Prevention | Building Permit |  | 2016-09-29 | 2 | OD | Rob Bloom
USB II | 00-03100.00 | 201600442 | 0193-003 | Cellular Site Work | Building Permit |  | 2016-04-15 | 2 | OD
Walker | 00-04339.00 | 201600741 | 0504-000 | 2nd Floor (Room 229) Reno | Building Permit | 2016-05-12 | 2016-05-20 | 2 | OD
Waring Hall | 00-02815.00 | 201600435 | 0272-000 | Dishroom Upgrades - Revision for Roof Fall Protection | Building Permit | 2016-03-18 | 2016-04-06 | 2 | OD
Wartik | 00-00471.04 | 201601345 | 0402-000 | Fire Protection Backflow Prevention | Building Permit |  | 2016-09-29 | 2 | OD | Rob Bloom
Water Treatment Plant | 05-92438.00 | 201600583 | 0918-001 | New Facility - Life Safety Revision | Building Permit |  | 2016-05-03 | 2 | OD | Rachel Prinkey
Water Treatment Plant | 05-92438.00 | 201601209 | 0918-001 | New Facility - Fire Alarm | C of O |  | 2016-08-30 | 2 | OD | Rachel Prinkey
Weaver | 00-04743.00 |  | 0109-000 | Campus Chilled Water Connection | Rejected | 2016-03-02 | 2016-03-30 | 1 | DS
Weaver | 00-04743.00 | 201600497 | 0109-000 | Campus Chilled Water Connect completed under (00-04841.00) | C of O | 2016-04-06 | 2016-04-12 | 2 | OD
White | 01-02630.15 | 201600514 | 0802-000 | ICA Single Point Entry Access Modifications- Resubmission | Building Permit | 2016-04-04 | 2016-04-15 | 2 | DS
White | 01-02630.15 | 201601093 | 0802-000 | ICA Single Point Entry Access Modification - Sprinklers | Building Permit |  | 2016-08-04 | 2 | OD
Whitmore Lab | 00-02635.00 | 201600774 | 0406-000 | Building Reno - 1st Floor Partial Occupancy | C of O |  | 2016-06-06 | 2 | OD
Whitmore Lab | 00-02635.00 | 201600772 | 0406-000 | Building Reno - 2nd Floor Partial Occupancy | C of O |  | 2016-06-06 | 2 | OD
Willard | 00-04718.00 | 201600011 | 0012-000 | Classroom 371 Reno | C of O | 2015-12-22 | 2016-01-12 | 2 | DS
Willard | 00-03953.00 | 201600012 | 0012-000 | Classroom 258 & 260 Reno | C of O | 2015-12-22 | 2016-01-12 | 2 | DS
Willard | 00-04748.00 | 201600756 | 0012-000 | Computer Lab 109 Reno | C of O | 2016-05-13 | 2016-05-27 | 2 | DS
Willard | 00-03406.00 | 201690509 | 0012-000 | Concrete Repairs in Stairwells | C of C |  | 2016-05-25 | 1 | OD
Willard | 03-41457.23 | 201600892 | 0012-000 | Telecom HUB Site Electrical & HVAC Upgrades | Building Permit | 2016-06-14 | 2016-06-24 | 2 | OD
Willard | 00-02463.00 | 201601125 | 0012-000 | Cross Connect Renovations | Building Permit | 2016-08-01 | 2016-08-08 | 2 | OD | Rob Bloom
Willard | 00-00471.04 | 201601352 | 0012-000 | Fire Protection Backflow Prevention | Building Permit |  | 2016-09-29 | 2 | OD | Rob Bloom

## Commonwealth
CAMPUS 2016 | PSU PROJECT # | Permit # | BLDG. # | DESCRIPTION | STATUS | DATE SENT | DATE RETURNED | PERMIT LEVEL | DS/OD
ABINGTON CAMPUS 0979-000
Lares Building | 00-04751.00 | 201690063 | 0979-005 | Roof Replacement | Building Permit |  | 2016-02-08 | 1 | OD
Lares Building | 00-04751.00 | 201600636 | 0979-005 | Roof Fall Protection | Building Permit | 2016-04-26 | 2016-05-11 | 2 | OD
Lares Building | 00-04985.00 |  | 0979-005 | Student Lounge Renovation | Rejected | 2016-06-13 | 2016-06-20 | 2 | OD
Lares Building | 00-04985.00 | 201601474 | 0979-005 | Student Lounge Renovation - Resubmission | Building Permit |  | 2016-11-10 | 2 | OD
Student Apartment | 00-02841.01 | 201601192 | 0979-012 | Sanitary Sewer Deficiency | Building Permit | 2016-08-18 | 2016-08-30 | 2 | OD
Student Apartment | 00-02841.00 | 201601248 | 0979-012 | New Building - Sprinkler | Building Permit | 2016-08-26 | 2016-09-09 | 2 | OD | Kyle Hollick
ALTOONA CAMPUS 0974-000
Eiche Library | 00-04529.00 | 201600307 | 0974-016 | 1st Floor Renovations | C of O | 2016-02-25 | 2016-03-10 | 2 | OD
Housing and Food Service Bldg | 00-05068.00 | 201601052 | 0974-007 | Port Sky Café - Special Diet Station | Building Permit | 2016-07-20 | 2016-07-25 | 2 | OD
Maple Hall | 00-04858.00 | 201600802 | 0974-008 | Toilet Room Renovations - Resubmission | Building Permit | 2016-05-18 | 2016-06-07 | 2 | OD
Maple Hall | 00-04858.00 | 201601160 | 0974-008 | Toilet Room Reno - Partial Occupancy | C of O | 2016-08-09 | 2016-08-11 | 2 | OD
Spruce Hall | 00-04299.00 | 201600397 | 0974-012 | Bathroom Renovations | C of O | 2016-03-14 | 2016-03-28 | 2 | OD
Stere Residence | 00-03935.00 |  | 0974-103 | Interior Renovations | No Permit Req. | 2016-04-14 |  | 2 | OD
Theatre Arts Studio | 00-04942.00 | 201601373 | 0974-077 | ACEL Lab Addition and Reno | Building Permit | 2016-09-09 | 2016-10-06 | 2 | OD
BEAVER CAMPUS 0986-000
Classroom Building | 00-03688.00 | 201600120 | 0986-006 | Roof Fall Protection | Building Permit | 2016-01-28 | 2016-02-09 | 2 | OD
Classroom Building | 00-03688.00 | 201690397 | 0986-006 | Roof Replacement | Building Permit | 2016-03-16 | 2016-04-18 | 1 | OD
Harmony Hall | 00-03387.00 | 201600937 | 0986-007 | Sport Court Pavilion | C of O | 2016-06-15 | 2016-06-28 | 2 | OD
Harmony Hall | 00-04855.00 |  | 0986-007 | Generator Replacement | Pending | 2016-10-19 |  | 2 | DS
Laboratory Classroom Building | 00-04227.00 |  | 0986-012/25 | Communication Services Building Addition | Rejected | 2016-04-07 | 2016-04-18 | 2 | OD
Laboratory Classroom Building | 00-04227.00 | 201600738 | 0986-012/25 | Communication Services Building Addition | Building Permit | 2016-05-11 | 2016-05-20 | 2 | OD
Laboratory Classroom Building | 00-04227.00 | 201600844 | 0986-012/25 | Communication Svc Bldg Addition - Revisions | C of O | 2016-06-03 | 2016-06-16 | 2 | OD
Michael Baker | 00-01873.01 | 201600823 | 0986-004 | Roof Fall Protection | Building Permit | 2016-06-02 | 2016-06-09 | 2 | OD
BEHREND CAMPUS 0972-000
Baseball Field | 00-04346.00 | 201600163 | 0972-145 | New Bleachers | C of O |  | 2016-02-12 | 2 | OD
Hammermill-Zurn | 00-03475.00 | 201600295 | 0972-022 | Emergency Generator Upgrade | Building Permit | 2016-02-25 | 2016-03-10 | 2 | DS
Kochel Center | N/A | 201690469 | 0972-085 | Room 169 & 170A Renovation | C of C | 2016-04-26 | 2016-05-16 | 1 | OD
Lilley Library | 00-04776.00 | 201600249 | 0972-030 | Study Room Renovations | C of O | 2016-02-18 | 2016-03-02 | 2 | OD
Elliot Hall | 00-03248.00 | 201601368 | 0972-074 | Gas Piping Replacement | Building Permit | 2016-09-23 | 2016-10-07 | 2 | OD
Yarnell Hall | 00-03248.00 | 201601367 | 0972-075 | Gas Piping Replacement | Building Permit | 2016-09-23 | 2016-10-07 | 2 | OD
Somers Hall | 00-03248.00 | 201601366 | 0972-076 | Gas Piping Replacement | Building Permit | 2016-09-23 | 2016-10-07 | 2 | OD
Caledonia/Turner Hall | 00-03248.00 | 201601364 | 0972-060 | Gas Piping Replacement | Building Permit | 2016-09-23 | 2016-10-07 | 2 | OD
Packett Hall | 00-03248.00 | 201601365 | 0972-061 | Gas Piping Replacement | Building Permit | 2016-09-23 | 2016-10-07 | 2 | OD
Ariel Hall | 00-03248.00 | 201601363 | 0972-062 | Gas Piping Replacement | Building Permit | 2016-09-23 | 2016-10-07 | 2 | OD
Champlain/Scorpion Hall | 00-03248.00 | 201601362 | 0972-063 | Gas Piping Replacement | Building Permit | 2016-09-23 | 2016-10-07 | 2 | OD
Reed Hall | 00-03248.00 | 201601369 | 0972-006 | Gas Piping Replacement | Building Permit | 2016-09-23 | 2016-10-07 | 2 | OD
BERKS CAMPUS 0980-000
Bowman Resident Center | 00-01593.00 |  | 0980-060 | Emergency Generator | Rejected | 2016-03-16 | 2016-04-01 | 2 | OD
Bowman Resident Center | 00-01593.00 | 201600672 | 0980-060 | Emergency Generator - Resubmission | Building Permit |  | 2016-05-25 | 2 | OD
Cedar Hall | 00-01593.00 |  | 0980-066 | Emergency Generator | Rejected | 2016-03-16 | 2016-04-01 | 2 | OD
Cedar Hall | 00-01593.00 | 201600671 | 0980-066 | Emergency Generator - Resubmission | Building Permit |  | 2016-05-25 | 2 | OD
Franco | 00-03097.00 | 201600306 | 0980-001 | HVAC & Lighting Upgrades | Building Permit | 2016-03-01 | 2016-03-10 | 2 | OD
Franco | 00-03097.00 | 201600907 | 0980-001 | HVAC & Lighting Upgrades | C of O |  | 2016-06-28 | 2 | OD
Franco | 00-03097.00 | 201601279 | 0980-001 | Telephone T123 Cooling Equipment Upgrades | Building Permit | 2016-09-09 | 2016-09-19 | 2 | OD
Gaige | 00-04735.00 | 201600597 | 0980-079 | Thermal Fluid Lab Renovations | Building Permit | 2016-04-14 | 2016-04-28 | 2 | OD
Greenbriar Hall | 00-01593.00 |  | 0980-065 | Emergency Generator | Rejected | 2016-03-16 | 2016-04-01 | 2 | OD
Greenbriar Hall | 00-01593.00 | 201600677 | 0980-065 | Emergency Generator - Resubmission | C of O |  | 2016-05-25 | 2 | OD
Laurel Hall | 00-01593.00 |  | 0980-061 | Emergency Generator | Rejected | 2016-03-16 | 2016-04-01 | 2 | OD
Laurel Hall | 00-01593.00 | 201600673 | 0980-061 | Emergency Generator - Resubmission | C of O |  | 2016-05-25 | 2 | OD
Oakmoss Hall | 00-01593.00 |  | 0980-062 | Emergency Generator | Rejected | 2016-03-16 | 2016-04-01 | 2 | OD
Oakmoss Hall | 00-01593.00 | 201600674 | 0980-062 | Emergency Generator - Resubmission | C of O |  | 2016-05-25 | 2 | OD
Perkins Student Center | 00-04075.00 | 201600530 | 0980-005 | HVAC System Upgrade | Building Permit |  | 2016-04-20 | 2 | OD
Perkins Student Center | 00-03785.00 | 201600810 | 0980-005 | IT Closet HVAC Upgrade | C of O | 2016-05-24 | 2016-06-09 | 2 | OD
Sage Hall | 00-01593.00 |  | 0980-064 | Emergency Generator | Rejected | 2016-03-16 | 2016-04-01 | 2 | OD
Sage Hall | 00-01593.00 | 201600676 | 0980-064 | Emergency Generator - Resubmission | C of O |  | 2016-05-25 | 2 | OD
Sweetwood Hall | 00-01593.00 |  | 0980-063 | Emergency Generator | Rejected | 2016-03-16 | 2016-04-01 | 2 | OD
Sweetwood Hall | 00-01593.00 | 201600675 | 0980-063 | Emergency Generator - Resubmission | C of O |  | 2016-05-25 | 2 | OD
BRANDYWINE CAMPUS 0989-000
Core Campus Walkways | 00-03122.00 | 201600027 | 0989-000 | Phase 3 of Walkways Rehab | C of O |  | 2016-04-08 | 2 | OD
Student Housing | 00-02839.01 | 201601147 | 0989-020 | New Residence Hall - Radon Piping/ Plan Revision | Buidling Permit | 2016-07-20 | 2016-08-11 | 2 | OD
Student Union | 00-03699.00 | 201601149 | 0989-091 | New Bldg - Radon Piping Revision | Buidling Permit |  | 2016-08-15 | 2 | OD | Hollick and Ritter
Student Union | 00-03699.00 | 201601423 | 0989-091 | New Bldg - Fire Alarm | Buidling Permit | 2016-09-20 | 2016-10-21 | 2 | OD
Student Union | 00-03699.00 | 201601370 | 0989-091 | New Bldg - Sprinkler | Buidling Permit |  | 2016-09-30 | 2 | OD
CAPITAL CAMPUS 0985-000
Capitol Union Building | N/A | 201600721 | 0985-011 | Kinesiology Lab Renovation | Building Permit | 2016-05-06 | 2016-05-20 | 2 | OD
Classroom Trailers | N/A | 201600679 | 0998-271 | Temporary Modular Building Modification | C of O | 2016-05-02 | 2016-05-16 | 2 | OD
Library & Classroom | 00-03298.00 | 201600031 | 0985-026 | Chiller Plant Upgrades | C of O | 2015-12-21 | 2016-01-12 | 2 | OD
Library & Classroom | N/A | 201600865 | 0985-026 | Second Floor Classroom | C of O | 2016-06-03 | 2016-06-20 | 2 | OD
Olmsted | 00-04024.00 | 201600398 | 0985-001 | Special Dining Renovations | C of O | 2016-03-15 | 2016-03-28 | 2 | OD
Olmsted | N/A | 201600724 | 0985-001 | 3rd Floor Offices Renovation | C of O | 2016-05-06 | 2016-05-20 | 2 | OD
Parking Lot on Olmsted Drive | 00-04521.00 | 201600516 | 0985-000 | Parking Lot Rehab | C of O | 2016-04-01 | 2016-04-20 | 2 | OD
Student Enrichment Ctr | 00-02222.01 | 201600501 | 0985-105 | New Construction - Fire Alarms | Building Permit |  | 2016-04-14 | 2 | OD
Student Enrichment Ctr | 00-02222.01 | 201600758 | 0985-105 | New Construction - Plan Revisions | Building Permit | 2016-05-17 | 2016-05-25 | 2 | OD
DICKINSON SCHOOL OF LAW-CARLISLE 0991-000
DUBOIS CAMPUS 0976-000
Hiller | 00-03332.00 |  | 0976-002 | Interior Renovations - Food Service Equipment | Rejected | 2016-02-26 | 2016-03-10 | 2 | OD
Hiller | 00-03332.00 | 201600594 | 0976-002 | Interior Reno - Food Service Equipment Resubmission | Building Permit | 2016-04-17 | 2016-04-28 | 2 | OD
Hiller | 00-03332.00 | 201601094 | 0976-002 | Interior Reno - Sprinklers | Building Permit |  | 2016-08-03 | 2 | OD
Hiller | 00-03332.00 | 201601151 | 0976-002 | Interior Reno - Fire Protection | Building Permit |  | 2016-08-16 | 2 | OD
FAYETTE CAMPUS 0984-000
Eberly | 00-03207.00 | 201600800 | 0984-001 | 3rd Floor Reno for EET & IST | Building Permit | 2016-05-06 | 2016-06-07 | 2 | OD
FRUIT RESEARCH CENTER 0986-020
Headhouse | 00-04808.00 | 201600437 | 0968-011 | Roof Fall Protection | C of O | 2016-03-22 | 2016-04-06 | 2 | OD
Headhouse | 00-04808.00 | 201690389 | 0968-011 | Roof Replacement | C of C | 2016-03-16 | 2016-04-18 | 1 | OD
Musselman | 00-04808.00 | 201690609 | 0968-020 | Roof Alterations | C of C | 2016-06-07 | 2016-06-23 | 1 | OD
GREAT VALLEY 0993-000
Conference Center (Safeguard Scientific) | 00-04502.00 | 201600033 | 0993-004 | New Signage at Conference Center | C of C | 2015-12-16 | 2016-01-12 | Sign | OD
Graduate Center | 00-04190.00 | 201600447 | 0993-001 | Toilet Room Renovations | Building Permit | 2016-03-18 | 2016-04-07 | 2 | OD
GREATER ALLEGHENY CAMPUS 0978-000
Crawford | 00-04844.00 | 201601174 | 0978-002 | Storefont/Interior Door Replacement | Building Permit | 2016-06-07 | 2016-08-18 | 2 | OD
Wunderley | 00-04098.00 | 201601176 | 0978-005 | Gymnasium Storefront Replacement | Building Permit | 2016-06-07 | 2016-08-18 | 2 | OD
Wunderley | 00-05177.00 | 201601276 | 0978-005 | Main Distribution Panel Replacement | Building Permit | 2016-09-01 | 2016-09-20 | 2 | DS
HAZELTON CAMPUS 0973-000
Bookstore | 00-04753.00 | 201690388 | 0973-013 | Roof Replacement | C of C | 2016-03-23 | 2016-04-18 | 1 | OD
Kostos Building | 00-01874.00 | 201600326 | 0973-009 | Building Reno | Building Permit | 2016-02-11 | 2016-03-16 | 2 | OD
Kostos Building | 00-01874.00 | 201601385 | 0973-009 | Building Reno - Plumbing Revision | Building Permit | 2016-09-28 | 2016-10-07 | 2 | OD
Kostos Building | 00-01874.00 |  | 0973-009 | Building Reno - Sprinkler | Pending | 2016-11-03 |  | 2 | OD
Modular Lab (Temporary) | 00-01874.00 | 201600235 | 0973-000 | Temp Swing Space for Kostos Reno-Resubmission | Building Permit | 2016-01-22 | 2016-02-29 | 2 | OD
Modular Lab (Temporary) | 00-01874.00 | 201600474 | 0973-000 | Temp Swing Space for Kostos Reno-Revisions | C of O |  | 2016-04-15 | 2 | OD
Physical Education Building | 00-03549.00 | 201601100 | 0973-004 | Roof Fall Protection | Building Permit | 2016-07-19 | 2016-08-03 | 2 | OD
New Athletic Field | 000-01171.00 | 201601135 | 0973-000 | New Soccer Field | Building Permit |  | 2016-08-08 | 2 | OD
HERSHEY 0990-000
LEHIGH VALLEY 0977-000
Academic Bldg | 00-04924.00 | 201600162 | 0977-100 | Room 307 Renovations | C of O | 2016-01-22 | 2016-02-16 | 2 | OD
Academic Bldg | 00-04926.00 | 201600628 | 0977-100 | Room 103 Renovations | Building Permit | 2016-04-21 | 2016-05-03 | 2 | OD
Academic Bldg | 00-05070.00 | 201600627 | 0977-100 | Room 305 Renovations | Building Permit | 2016-04-21 | 2016-05-11 | 2 | OD
Academic Bldg | 00-03440.00 | 201600779 | 0977-100 | Data/Telecom Emergency Power Upgrades | Building Permit | 2016-05-13 | 2016-06-01 | 2 | OD
Academic Bldg | 00-05243.00 | 201601184 | 0977-100 | Room 155 Renovations | C of O | 2016-08-15 | 2016-08-22 | 2 | OD
Academic Bldg | 00-05302.00 | 201601291 | 0977-100 | Finance/Registration Reno | Building Permit | 2016-09-15 | 2016-09-20 | 2 | OD
MONT ALTO CAMPUS 0970-000
Foods | 00-04296.00 | 201600607 | 0971-018 | HVAC & Heritage Rm Improvements | C of O |  | 2016-05-02 | 2 | OD
General Studies Bldg | 00-04822.00 |  | 0971-001 | Elevator Tower Structural Rehab | Rejected | 2016-01-29 | 2016-03-01 | 1 | OD
General Studies Bldg | 00-04822.00 | 201600352 | 0971-001 | Elevator Tower Structural Rehab - Resubmission | C of O | 2016-03-08 | 2016-03-24 | 2 | OD
Library | 00-04905.00 | 201600290 | 0971-019 | Storefront Replacement | C of O | 2016-02-25 | 2016-03-15 | 2 | OD
Multipurpose Activities Center | 00-05111.00 | 201600976 | 0971-021 | HVAC Upgrade AHU-1 Weight Room | Building Permit | 2016-06-28 | 2016-07-12 | 2 | OD
Wiestling Hall | 00-04729.00 |  | 0971-003 | Porch Replacement | Rejected | 2016-02-25 | 2016-03-17 | 2 | OD
Wiestling Hall | 00-04729.00 | 201600535 | 0971-003 | Porch Replacement - Resubmission | Building Permit | 2016-04-06 | 2016-04-20 | 2 | OD
NAVY YARD
EEB HUB 661 | N/A | 201600108 | 0998-269 | Skylight Replacement | Building Permit | 2016-01-21 | 2016-02-03 | 2 | OD
CBEEI (Building 7R) | 00-05045.00 | 201600875 | 0999-091 | Roof-mounted Solar Array | Building Permit | 2016-05-02 | 2016-06-20 | 2 | OD
NEW KENSINGTON 0981-000
Science Bldg | 00-04968.00 | 201690261 | 0981-001 | Gas Line Extension | Building Permit | 2016-03-03 | 2016-03-22 | 1 | DS
ROCK SPRINGS 0959-000
SCHUYLKILL CAMPUS 0975-000
Administration | 00-04120.00 | 201600703 | 0975-006 | HVAC System Replacement | Building Permit | 2016-04-28 | 2016-05-16 | 2 | OD
Administration | 00-04120.00 | 210690601 | 0975-006 | Lighting Fixture Replacement | Building Permit | 2016-05-19 | 2016-06-10 | 1 | OD
Health and Wellness Center | 00-03492.00 | 201600452 | 0975-001 | Health and Wellness Renovations | C of O | 2016-03-24 | 2016-04-07 | 2 | OD
Health and Wellness Center | 00-03441.00 | 201600688 | 0975-001 | Refuge Power Upgrade | Building Permit | 2016-05-04 | 2016-05-16 | 2 | OD
SHAVERS CREEK 0960-000
Temporary Trailer | 00-04020.00 |  | 0960-000 | Temporary Trailer for Swing Space | Rejected | 2016-05-19 | 2016-06-20 | 2 | OD
Environmental Center | 00-04020.00 |  | 0960-001 | Building Addition and Renovation | Rejected | 2016-05-23 | 2016-06-20 | 2 | OD
Campbell Center | 00-04020.00 | 201600909 | 0960-008 | Building Demolition | Demo Permit |  | 2016-06-23 | Demo | OD
Storage Building | 00-04020.00 | 201600908 | 0960-004 | Building Demolition | Demo Permit |  | 2016-06-23 | Demo | OD
Office Building | 00-04020.00 | 201600911 | 0960-007 | Building Demolition | Demo Permit |  | 2016-06-23 | Demo | OD
| 00-04020.00 | 201600910 | 0960-019 | Building Demolition | Demo Permit |  | 2016-06-23 | Demo | OD
SHENANGO CAMPUS
WARMINSTER 0998-000
WILKES-BARRE CAMPUS 0983-000
Science Center | 00-03589.00 |  | 0983-004 | Chemistry Lab Renovations | Rejected |  | 2016-03-01 | 2 | OD
Science Center | 00-03589.00 | 201600752 | 0983-004 | Chemistry Lab Renovations-Resubmission | Building Permit |  | 2016-05-25 | 2 | OD
Science Center | 00-04986.00 | 201600945 | 0983-004 | Boiler Replacement | Building Permit |  | 2016-06-27 | 2 | OD
WORTHINGTON-SCRANTON CAMPUS 0982-000
Dawson | 00-03446.00 |  | 0982-001 | Generator Replacement | Rejected | 2016-03-15 | 2016-04-01 | 2 | DS
Dawson | 00-03446.00 | 201601161 | 0982-001 | Generator Replacement | Building Permit | 2016-08-03 | 2016-08-16 | 2 | DS
Dawson | 00-04750.00 | 201600391 | 0982-001 | Parking Lot and Roadway Rehab | C of O |  | 2016-03-29 | 2 | OD
Dawson | 00-04950.00 | 201600801 | 0982-001 | First Floor Renovations | Building Permit | 2016-05-23 | 2016-06-07 | 2 | OD
Dawson | 00-04951.00 |  | 0982-001 | Room 10 Renovation | Rejected | 2016-06-02 | 2016-06-14 | 2 | OD
Dawson | 00-04951.00 | 201600924 | 0982-001 | Room 10 Renovation | Building Permit |  | 2016-07-01 | 2 | OD
Classroom Library | 00-04750.00 | 201600393 | 0982-002 | Parking Lot and Roadway Rehab | C of O |  | 2016-03-29 | 2 | OD
Multi-purpose | 00-04750.00 | 201600392 | 0982-003 | Parking Lot and Roadway Rehab | C of O |  | 2016-03-29 | 2 | OD
Study-Learning Ctr | 00-04952.00 |  | 0982-004 | Sherbine Lounge Renovation | Rejected | 2016-06-02 | 2016-06-14 | 2 | OD
Study-Learning Ctr | 00-04952.00 | 201600926 | 0982-004 | Sherbine Lounge Renovation | Building Permit |  | 2016-07-01 | 2 | OD
YORK CAMPUS 0964-000
Romano (Conference Center) | 00-04946.00 | 201600657 | 0964-001 | Lecture Room Upgrades | Building Permit | 2016-04-28 | 2016-05-11 | 2 | OD
Romano | 00-05180.00 | 201690725 | 0964-001 | Boiler Replacement | Building Permit | 2016-06-29 | 2016-07-15 | 1 | OD
Ruhl Student Community Center | 00-02344.01 | 201600587 | 0964-005 | Building Addition and Reno - Fire Alarm | C of O |  | 2016-05-03 | 2 | OD
Ruhl Student Community Center | 00-02344.01 | 201600626 | 0964-005 | Building Addition and Reno - Sprinkler | C of O |  | 2016-05-13 | 2 | OD
Ruhl Student Community Center | 00-02344.01 | 201601066 | 0964-005 | Bldg Add & Reno - plan revision | C of O | 2016-07-21 | 2016-07-28 | 2 | OD
Ruhl Student Community Center | 00-02344.01 | 201601070 | 0964-005 | Bldg Add & Reno - ampitheater | C of O | 2016-07-21 | 2016-07-28 | 2 | OD
Ruhl Student Community Center | 00-02344.01 | 201601068 | 0964-005 | Bldg Add & Reno - Roof Anchor | Building Permit | 2016-07-21 | 2016-07-29 | 2 | OD
WARMINSTER 0998-004
Navigation Center |  | 201601232 | 0998-004 | Scorsby Lab Electrical Upgrades | Building Permit |  | 2016-09-15 | 2 | OD | Bob Cain
995 Newton Rd |  | 201601452 |  | New Modular Office Space | Building Permit | 2016-09-07 | 2016-11-02 | 2 | OD | Bob Cain